## Report Generator
Module | Tasks | Sub Tasks | Notes | Target Completion Date
Report Module
Analysis
|  |  | <Parallel Task> | TBD
Environment Setup
|  | Docker Setup with Alexa server integration to run Node.js application |  | 2018-10-01
|  | AWS Resource Setup [Aws Account, RDS, S3 Bucket, Lambda] |  | 2018-12-01
|  | Version Control Setup for Codebase |  | 2018-12-01
Prerequisites
|  | Existing/Old Report data for our use case | We need the sample old report used in the organization and on the basis of that report, we will create our use case. Also our DB strucutre will depend on the same.
POC
|  | Node Js Application integration with Alexa and Run a sample application on our environment. |  | 16/1/2018
|  | Generate billing information Report for aws account | We will do this POC on our custom account first. Once successful then we need the organization setup strucutre of aws account so that we can process for our Main use case which is "Generate a report from subaccount for main/billing account". | TBD
Meeting [Discussion and Feedback]
|  | Meeting to finalize the project Flow. | We need to connect with someone to finalize and proceed further. | 17/1/2018
Design
|  | Design Appraoch Finalize |  | TBD
Development Tasks
|  | Authentication |  | TBD
|  | Database strucuture and tables creation |  | TBD
|  | Prepare Interaction model for Alexa [Intent and Utterances] |  | TBD
|  | Create New Alexa Skill/App - [Create Service Endpoint(Using node Js) , Integrate with DB and Deployment] |  | TBD
|  | Integration of Echo dot with Alexa Skill [Assignment and configuration] |  | TBD
|  | Unit Testing |  | TBD